## Gantt Chart
LendLink — Peer Lending Platform ¦ Project Gantt Chart ¦ March 10 – June 15, 2025
Hansini Kawindi (2577506) Aale Magar Rijan (2577510) Shivakoti Pawan (2577509) Karki Kshetri Surjeet (2577511) | [7 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
[8 empty] | 10 Mar | 17 Mar | 24 Mar | 31 Mar | 07 Apr | 14 Apr | 21 Apr | 28 Apr | 05 May | 12 May | 19 May | 26 May | 02 Jun | 09 Jun
# | Owner | Task Description | Member | Priority | Status | Sw | Ew
▌ Hansini Kawindi (2577506)
Phase 1 — Project Setup & Data Foundation
1 |  | Project requirements analysis, team task distribution | All 4 Members | Critical | Completed | 1 | 1
2 |  | Firebase project: Auth, RTDB, Storage, Cloud Messaging | Hansini | Critical | Completed | 1 | 2 | bar: W1 10 Mar to W2 17 Mar
3 |  | Firebase Realtime DB schema — all 12 node paths designed | Hansini | Critical | Completed | 2 | 2
4 |  | Data models: User, Item, BorrowRecord, Wallet, Histories | Hansini | Critical | Completed | 2 | 3 | bar: W2 17 Mar to W3 24 Mar
5 |  | AppDatabase.kt — Room DB, 6 entities, 6 DAOs | Hansini | High | Completed | 3 | 4
Phase 2 — Authentication Module (All Screens)
6 |  | AuthRepository.kt — register, login, wallet init, signOut | Hansini | Critical | Completed | 3 | 4 | bar: W3 24 Mar to W4 31 Mar
7 |  | Register screen — all fields, location picker, role select | Hansini | High | Completed | 4 | 5
8 |  | Login screen — email/password, role routing, error states | Hansini | Critical | Completed | 4 | 5 | bar: W4 31 Mar to W5 07 Apr
9 |  | Username uniqueness check against Firebase /usernames/ | Hansini | Critical | Completed | 5 | 5
10 |  | Bug fix: signOut() after register → redirect to Login | Hansini | Critical | Completed | 12 | 12 | bar: W12 26 May
|  | ★ ★ MILESTONE: Auth end-to-end working on device | All 4 Members | Milestone | Milestone | 5 | 5 | bar: W1 10 Mar to W14 09 Jun
Phase 5 — Lender History Screens
12 |  | Lender Credit History screen (borrow + penalty entries) | Hansini | High | Completed | 10 | 10 | bar: W10 12 May
13 |  | Lender Lend History — completed lends, borrower contact | Hansini | High | Completed | 10 | 11
Phase 6 — Browse Items (New Feature)
14 |  | Browse Items page — empty-state trigger, all-lenders grid | Hansini | High | Completed | 11 | 11 | bar: W11 19 May
15 |  | Browse Item Detail — name, price, desc, lender phone/loc | Hansini | High | Completed | 11 | 12
▌ Aale Magar Rijan (2577510)
Phase 3a — Lender Dashboard & Item Listing
16 |  | Lender Dashboard — Available tab, tab bar, wallet card | Rijan | Critical | Completed | 4 | 5 | bar: W4 31 Mar to W5 07 Apr
17 |  | Lender Dashboard — Lent tab, pending-return banner | Rijan | High | Completed | 5 | 6
18 |  | Category filter chips, real-time item list via Firebase | Rijan | High | Completed | 5 | 6 | bar: W5 07 Apr to W6 14 Apr
Phase 3b — Add / Edit / Delete Items
19 |  | Add Item screen — CameraX photo, name, price, category | Rijan | Critical | Completed | 6 | 7
20 |  | ItemRepository.kt — add/update/delete + Storage upload | Rijan | Critical | Completed | 6 | 7 | bar: W6 14 Apr to W7 21 Apr
21 |  | Available item detail — full view, Edit & Delete buttons | Rijan | High | Completed | 7 | 7
22 |  | No edit/delete in Lent tab — read-only enforcement | Rijan | High | Completed | 7 | 7 | bar: W7 21 Apr
Phase 3c — Category Manager
23 |  | Category Manager — add, rename, delete categories | Rijan | High | Completed | 7 | 8
24 |  | In-use protection — block delete if category has items | Rijan | High | Completed | 8 | 8 | bar: W8 28 Apr
25 |  | Auto-delete empty category after last item removed | Rijan | Medium | Completed | 8 | 8
|  | ★ ★ MILESTONE: All Lender Screens functional | All 4 Members | Milestone | Milestone | 8 | 8 | bar: W8 28 Apr
Phase 4a — QR Code System
27 |  | QR Code generation — ZXing QRCodeWriter 512×512, modal | Rijan | Critical | Completed | 8 | 9
28 |  | QR Scanner — ZXing CompoundBarcodeView, camera permission | Rijan | Critical | Completed | 9 | 9 | bar: W9 05 May
29 |  | Scan → fetch item from Firebase → Borrow Confirm dialog | Rijan | Critical | Completed | 9 | 10
Phase 8 — Google Play Store Deployment
30 |  | Generate release keystore, SHA-1 fingerprint → Firebase | Surjeet | Critical | Completed | 13 | 13
31 |  | Google Play Console — content, data safety, Internal Testing | Surjeet | Critical | Completed | 14 | 14 | bar: W14 09 Jun
32 |  | Professor evaluation — install from Play Store link | All 4 Members | Critical | In Progress | 14 | 14
33 |  | Project docs: Gantt, RTM, Mockups, Setup Guide | All 4 Members | High | Completed | 13 | 14 | bar: W13 02 Jun to W14 09 Jun
|  | ★ ★ MILESTONE: App published & professor evaluation done | All 4 Members | Milestone | Milestone | 14 | 14 | bar: W1 10 Mar to W14 09 Jun
▌ Shivakoti Pawan (2577509)
Phase 2b — Splash & App Shell
34 |  | Splash screen — 3-sec animated sky-blue intro, spring | Pawan | Medium | Completed | 4 | 5 | bar: W4 31 Mar to W5 07 Apr
35 |  | MainActivity, NavGraph, MVVM architecture skeleton | Pawan | Critical | Completed | 3 | 4
Phase 4b — Borrower Dashboard & Item Screens
36 |  | Borrower Dashboard — teal wallet, active borrows list | Pawan | Critical | Completed | 9 | 10 | bar: W9 05 May to W10 12 May
37 |  | Borrower item detail — lender contact, deadline, overdue | Pawan | High | Completed | 10 | 10
38 |  | Status chips — Borrowed / Overdue / Return Pending | Pawan | High | Completed | 10 | 10 | bar: W10 12 May
39 |  | Borrow Confirm dialog — item, price, 7-day deadline note | Pawan | Critical | Completed | 9 | 9
|  | ★ ★ MILESTONE: All Borrower Screens functional | All 4 Members | Milestone | Milestone | 11 | 11 | bar: W11 19 May
Phase 6 — WorkManager Background Tasks
40 |  | DeadlineCheckWorker — 24h reminder push notification | Pawan | High | Completed | 11 | 12
41 |  | DeadlineCheckWorker — hourly countdown when ≤10h remain | Pawan | High | Completed | 12 | 12 | bar: W12 26 May
42 |  | PenaltyWorker — daily ₩5,000 deduction, credit lender | Pawan | High | Completed | 12 | 12
43 |  | WorkerScheduler — enqueueUniquePeriodicWork on launch | Pawan | Medium | Completed | 12 | 12 | bar: W12 26 May
|  | ★ ★ MILESTONE: Background workers verified on device | All 4 Members | Milestone | Milestone | 12 | 12 | bar: W1 10 Mar to W14 09 Jun
Phase 7a — Testing & Bug Fixes (Pawan)
44 |  | Bug fix: logout clears full backstack (no crash on back) | Pawan | Critical | Completed | 13 | 13 | bar: W13 02 Jun
45 |  | Build release AAB, proguard rules, Play Store prepare | Pawan | High | Completed | 13 | 14
▌ Karki Kshetri Surjeet Singh (2577511)
Phase 4c — Borrow Transaction Logic
46 |  | BorrowRepository — borrowItem(): check credits, deduct, credit lender | Surjeet | Critical | Completed | 9 | 10 | bar: W9 05 May to W10 12 May
47 |  | Wallet nodes per user /wallets/{uid}/balance (not shared) | Surjeet | Critical | Completed | 10 | 10
48 |  | Lent item detail — borrower contact info & send reminder | Surjeet | High | Completed | 10 | 10 | bar: W10 12 May
Phase 4d — Return Flow
49 |  | Two-step return — requestReturn() → lender accepts | Surjeet | Critical | Completed | 10 | 11
50 |  | acceptReturn() — item → Available, write Lend/Borrow History | Surjeet | Critical | Completed | 11 | 11 | bar: W11 19 May
Phase 5 — Borrower History Screens & Notifications
51 |  | Borrower Payment History — borrow + penalty payment log | Surjeet | High | Completed | 11 | 11
52 |  | Borrower Borrow History — returned items, lender contact | Surjeet | High | Completed | 11 | 12 | bar: W11 19 May to W12 26 May
53 |  | FCM push — LendLinkMessagingService, all 5 notif types | Surjeet | High | Completed | 11 | 12
54 |  | In-app Notifications screen — 5 types with icons | Surjeet | Medium | Completed | 12 | 12 | bar: W12 26 May
Phase 7b — Testing & Bug Fixes (Surjeet)
55 |  | Bug fix: itemId generated BEFORE photo upload | Surjeet | Critical | Completed | 12 | 13
56 |  | Bug fix: 16 KB page size — useLegacyPackaging=false | Surjeet | High | Completed | 13 | 13 | bar: W13 02 Jun
57 |  | Multi-device integration testing (lender ↔ borrower) | All 4 Members | Critical | Completed | 13 | 13
58 |  | ★ ★ MILESTONE: All tests passed — App stable | All 4 Members | Milestone | Milestone | 13 | 13 | bar: W13 02 Jun
59 |  | Project docs: Gantt, RTM, Mockups, Setup Guide | All 4 Members | High | Completed | 13 | 14 | bar: W13 02 Jun to W14 09 Jun
|  | ★ ★ MILESTONE: App published & professor evaluation done | All 4 Members | Milestone | Milestone | 14 | 14 | bar: W1 10 Mar to W14 09 Jun
LEGEND
Hansini – Green
Rijan - Purple
Pawan - Orange
Surjeet - Teal
Completed
In-Progress
◆ | Milestone

## RTM
LendLink — Requirements Traceability Matrix (RTM)
March 10 – June 15, 2025 · Hansini Kawindi (2577506) · Aale Magar Rijan (2577510) · Shivakoti Pawan (2577509) · Karki Kshetri Surjeet Singh (2577511)
Req ID | Category | Requirement | Priority | Phase & Date | Module / File | Test Case(s) | Assigned | Status | Verification
▌ Hansini Kawindi (2577506) — Auth · Data Models · Room DB · Credit/Lend History · Browse Items
FR-01 | Authentication | New users register with unique username, email, phone, password, location & role (Lender / Borrower) | Critical | Phase 2 · W3–W4 (Mar 24 – Apr 6) | AuthRepository.kt – register(); RegisterScreen composable | TC-01: Valid data → account created TC-02: Duplicate username → 'Username already taken' | Hansini | Completed | Manual + Firebase Console
FR-02 | Authentication | Username uniqueness validated against Firebase /usernames/ index node before creating account | Critical | Phase 2 · W4 (Mar 31 – Apr 6) | AuthRepository.kt – db.child('usernames').get().await() | TC-03: Existing username → registration blocked with error message | Hansini | Completed | Manual Testing
FR-03 | Authentication | User location (address, lat, lng) captured in Register and stored in Firebase /users/{uid} | High | Phase 2 · W3–W4 (Mar 24 – Apr 6) | RegisterScreen – LocationPickerDialog; Firebase /users/{uid}/locationAddress | TC-04: Enter location → check /users/{uid}/locationAddress in Firebase console | Hansini | Completed | Firebase Console
FR-04 | Authentication | After registration, user is redirected to Login screen (NOT auto-directed to dashboard) | Critical | Phase 2 · W4 (Mar 31 – Apr 6) | AuthRepository.kt – auth.signOut() after register(); NavGraph routing | TC-05: Complete registration → Login screen visible, no dashboard opens | Hansini | Completed | Manual Testing
FR-05 | Authentication | Firebase Auth email/password login routes user to Lender Dashboard or Borrower Dashboard based on role | Critical | Phase 2 · W4 (Mar 31 – Apr 6) | AuthRepository – login(); NavGraph.kt – role-based route selection | TC-06: Lender login → LenderDashboard TC-07: Borrower login → BorrowerDashboard | Hansini | Completed | Manual Testing
FR-06 | Authentication | Unregistered email login shows error Snackbar: 'Account not found — please register' | High | Phase 2 · W4 (Mar 31 – Apr 6) | LoginScreen composable – error state Snackbar | TC-08: Login with unknown email → red Snackbar at bottom of screen | Hansini | Completed | Manual Testing
FR-07 | Data Models | Data models fully defined: User (with location), Item (with lender/borrower fields), BorrowRecord, Wallet | Critical | Phase 1 · W2–W3 (Mar 17 – Mar 30) | Models.kt – all data classes with correct field types | TC-09: Create user, item, and record in Firebase → verify all fields persisted | Hansini | Completed | Firebase Console
FR-08 | Room DB | Room DB (AppDatabase.kt) provides offline cache for all 6 entities via 6 separate DAOs | High | Phase 2 · W3–W4 (Mar 24 – Apr 6) | AppDatabase.kt – 6 entities, 6 DAOs, fallbackToDestructiveMigration | TC-10: Load data online → enable airplane mode → data still visible | Hansini | Completed | Manual Testing (airplane mode)
FR-09 | Lender History | Lender Credit History logs each borrow: '₩X received from [Borrower] for borrowing [Item]' | High | Phase 5 · W10 (May 12 – May 18) | LenderHistoryScreens.kt – LenderCreditHistoryScreen; BorrowRepository writes to lender_credit_history | TC-11: Item borrowed → entry appears with correct borrower name, item, amount | Hansini | Completed | Manual Testing
FR-10 | Lender History | Lender Credit History logs penalties: '₩X penalty received from [Borrower] for returning [Item] late' | High | Phase 5 · W10 (May 12 – May 18) | BorrowRepository – applyPenalty() writes LenderCreditHistory entry | TC-12: Penalty fires → penalty entry appears in Credit History screen | Hansini | Completed | Manual Testing
FR-11 | Lender History | Lend History shows completed lends only (post return-accepted) with borrower phone and location | High | Phase 5 · W10–W11 (May 12 – May 25) | LenderHistoryScreens.kt – LendHistoryScreen; acceptReturn() writes to lend_history | TC-13: Accept return → LendHistory card shows borrower phone and location | Hansini | Completed | Manual Testing
FR-12 | Browse Items | When borrower has zero active borrows, empty state shows 'Browse Available Items' button | High | Phase 6 · W11 (May 19 – May 25) | BorrowerDashboard – empty state composable with Browse CTA | TC-14: New borrower with no borrows → Browse button visible on dashboard | Hansini | Completed | Manual Testing
FR-13 | Browse Items | Browse Items page shows ALL available items from ALL lenders — photo, name, price, lender location | High | Phase 6 · W11 (May 19 – May 25) | BrowseItemsScreen; Firebase /items query filtered status='available' | TC-15: 2 lenders add items → Browse page shows items from both simultaneously | Hansini | Completed | Multi-device Testing
FR-14 | Browse Items | Tapping a Browse item opens full detail: image, name, price, description, lender name, phone, location | High | Phase 6 · W11–W12 (May 19 – Jun 1) | BrowseItemDetailScreen – all item + lender contact fields displayed | TC-16: Tap browse item → all lender contact details visible | Hansini | Completed | Manual Testing
▌ Aale Magar Rijan (2577510) — Lender Dashboard · Items · QR Code · Category Manager
FR-15 | Lender – Dashboard | Lender Dashboard shows wallet card with THIS lender's own earnings only (not a shared balance) | Critical | Phase 3 · W4–W5 (Mar 31 – Apr 13) | LenderDashboard.kt – wallet card; BorrowRepository – observeWallet(uid) | TC-17: Two lenders on separate devices → each sees only own balance | Rijan | Completed | Multi-device Testing
FR-16 | Lender – Dashboard | Dashboard has Available tab (ready items) and Lent tab (borrowed items), updating in real-time | Critical | Phase 3 · W4–W5 (Mar 31 – Apr 13) | LenderDashboard.kt – TabRow; Firebase ValueEventListener on /items | TC-18: Borrow event → item moves from Available to Lent tab instantly without refresh | Rijan | Completed | Multi-device Testing
FR-17 | Lender – Dashboard | Category filter chips appear at top of Available tab; selecting a chip filters the list | High | Phase 3 · W5–W6 (Apr 7 – Apr 20) | LenderDashboard – chipsRow composable; LenderViewModel.filteredItems StateFlow | TC-19: Tap 'Electronics' chip → only Electronics items shown | Rijan | Completed | Manual Testing
FR-18 | Lender – Dashboard | Yellow pending-return banner appears when borrower submits return; tapping it switches to Lent tab | High | Phase 3 · W5–W6 (Apr 7 – Apr 20) | LenderDashboard – pendingReturns StateFlow; banner tap navigates to Lent tab | TC-20: Borrower taps Request Return → yellow banner appears on lender dashboard | Rijan | Completed | Multi-device Testing
FR-19 | Lender – Items | Lender adds items with: name, description, price (KRW), category, and CameraX photo | Critical | Phase 3 · W6–W7 (Apr 14 – Apr 27) | AddItemScreen composable; CameraX integration; ItemRepository – addItem() | TC-21: Fill form + take CameraX photo + Publish → item appears in Available tab with photo | Rijan | Completed | Manual Testing
FR-20 | Lender – Items | Lender can edit name, description, price, category, and replace photo from Available tab | High | Phase 3 · W7 (Apr 21 – Apr 27) | AddItemScreen (edit mode); ItemRepository – updateItem() | TC-22: Edit price → check Firebase /items/{itemId}/price updated correctly | Rijan | Completed | Firebase Console
FR-21 | Lender – Items | Lender can delete available items; deletion blocked when item is currently lent | High | Phase 3 · W7 (Apr 21 – Apr 27) | ItemRepository – deleteItem() with status check; LenderAvailableDetailScreen | TC-23: Delete available → removed TC-24: Delete lent item → error Snackbar shown | Rijan | Completed | Manual Testing
FR-22 | Lender – Items | No edit or delete controls shown in Lent tab — lent items are read-only | High | Phase 3 · W7 (Apr 21 – Apr 27) | LenderScreens – LentTab composable (no action buttons rendered for lent items) | TC-25: Open any lent item → confirm no Edit or Delete buttons are present | Rijan | Completed | Manual Testing
FR-23 | Category Manager | Lender can add, rename, and delete custom categories via Category Manager | High | Phase 3 · W7–W8 (Apr 21 – May 4) | CategoryManagerScreen; ItemRepository – addCategory(), editCategory(), deleteCategory() | TC-26: Add 'Cameras' → appears in dropdown TC-27: Rename → updated everywhere | Rijan | Completed | Manual Testing
FR-24 | Category Manager | Deleting a category that has items is blocked with error: 'Category is currently in use' | High | Phase 3 · W8 (Apr 28 – May 4) | ItemRepository – deleteCategory() checks item count before deletion | TC-28: Delete category with 2 items → error Snackbar; category unchanged | Rijan | Completed | Manual Testing
FR-25 | Category Manager | When the last item in a category is deleted, the category auto-removes from Firebase | Medium | Phase 3 · W8 (Apr 28 – May 4) | ItemRepository – checkAndDeleteEmptyCategory() called after each item deletion | TC-29: Delete last item in category → category disappears from filter chips | Rijan | Completed | Manual Testing
FR-26 | QR Code | Lender generates a QR code per item encoding its unique itemId; displayed in a modal dialog | Critical | Phase 4 · W8–W9 (Apr 28 – May 11) | LenderAvailableDetailScreen – ZXing QRCodeWriter, 512×512 Bitmap, AlertDialog | TC-30: Tap 'Generate QR' → QR image shown in dialog with item name below | Rijan | Completed | Manual Testing
FR-27 | QR Code | Borrower QR scanner uses ZXing CompoundBarcodeView with camera permission handling | Critical | Phase 4 · W9 (May 5 – May 11) | ScanQRScreen – CompoundBarcodeView; Accompanist rememberPermissionState | TC-31: Open scanner → camera feed + targeting overlay shown TC-32: Deny permission → Grant button | Rijan | Completed | Device Testing
FR-28 | QR Code | On QR detection, system fetches item from Firebase and shows Borrow Confirm dialog with full details | Critical | Phase 4 · W9–W10 (May 5 – May 18) | BorrowerViewModel – fetchItem(itemId); ScanQRScreen – BorrowConfirmDialog | TC-33: Scan valid QR → dialog shows item name, lender, price, 7-day deadline | Rijan | Completed | Multi-device Testing
▌ Shivakoti Pawan (2577509) — Splash · MVVM Shell · Borrower UI · WorkManager · Bug Fixes
FR-29 | App Shell | MainActivity sets up Splash Screen API, WorkManager scheduler, and NavHost | Critical | Phase 2 · W3–W4 (Mar 24 – Apr 6) | MainActivity.kt – SplashScreen.installSplashScreen(); WorkerScheduler.schedule() | TC-34: App launches → splash animates → correct dashboard shown | Pawan | Completed | Manual Testing
FR-30 | Splash Screen | 3-second animated sky-blue splash: chain-link logo scales in 0.5→1.0 with spring physics | Medium | Phase 2 · W4–W5 (Mar 31 – Apr 13) | SplashScreen.kt – Animatable, spring() spec, alpha fade out after 3s | TC-35: Install app → splash displays LendLink logo animation then navigates | Pawan | Completed | Device Testing
FR-31 | Borrower – Dashboard | Borrower Dashboard shows teal wallet card with borrower's own credits (₩100,000 at registration) | Critical | Phase 4 · W9–W10 (May 5 – May 18) | BorrowerDashboard.kt – teal wallet card; /wallets/{uid}/balance initialised in register | TC-36: Register as Borrower → check /wallets/{uid}/balance = 100000 in Firebase | Pawan | Completed | Firebase Console
FR-32 | Borrower – Dashboard | Active borrows listed with status chips: Borrowed (orange), Overdue (red), Return Pending (blue) | High | Phase 4 · W10 (May 12 – May 18) | BorrowerDashboard – BorrowedCard composable; status-driven chip colour logic | TC-37: Active → orange TC-38: Past deadline → red TC-39: After request → blue | Pawan | Completed | Manual Testing
FR-33 | Borrower – Detail | Borrower item detail shows lender's name, phone number, and location address | High | Phase 4 · W10 (May 12 – May 18) | BorrowerItemDetailScreen – Lender Details section with all contact fields | TC-40: Open borrowed item → lender name, phone, location all visible | Pawan | Completed | Manual Testing
FR-34 | Borrower – Detail | Borrow Confirm dialog shows item, lender, price, 7-day deadline, and exact deduction note | Critical | Phase 4 · W9 (May 5 – May 11) | BorrowConfirmDialog composable – all item + lender fields + '₩X will be deducted' note | TC-41: After QR scan → confirm dialog shows all info before borrowing | Pawan | Completed | Multi-device Testing
FR-35 | WorkManager | DeadlineCheckWorker runs every 1 hour and sends ONE push when 24 hours remain before deadline | High | Phase 6 · W11–W12 (May 19 – Jun 1) | Workers.kt – DeadlineCheckWorker; PeriodicWorkRequest(1h) | TC-42: Set deadline 24h from now → push notification received within 1 hour | Pawan | Completed | Device Testing
FR-36 | WorkManager | DeadlineCheckWorker sends hourly notifications when ≤10 hours remain: '⚠ Xh Left to Return' | High | Phase 6 · W12 (May 26 – Jun 1) | Workers.kt – DeadlineCheckWorker countdown branch (hoursLeft <= 10) | TC-43: Deadline within 10h → hourly notification with correct countdown | Pawan | Completed | Device Testing
FR-37 | WorkManager | PenaltyWorker runs every 24 hours: deducts ₩5,000 from borrower, credits lender for overdue items | High | Phase 6 · W12 (May 26 – Jun 1) | Workers.kt – PenaltyWorker; BorrowRepository.applyPenalty(record, 5000L) | TC-44: Item overdue > 24h → borrower −₩5,000, lender +₩5,000 in Firebase | Pawan | Completed | Manual (time manipulation)
FR-38 | Bug Fix | Logout clears the full navigation backstack (popUpTo(0) inclusive=true) — no back-button crash | Critical | Phase 7 · W13 (Jun 2 – Jun 8) | NavGraph.kt – goLogin() { popUpTo(0) { inclusive = true } } | TC-45: Full session → logout → press Back multiple times → app never crashes | Pawan | Completed | Device Testing
▌ Karki Kshetri Surjeet Singh (2577511) — Transactions · Return Flow · Notifications · Deployment
FR-39 | Transaction | Confirm borrow: deduct price from borrower, credit lender, create BorrowRecord, set item to 'lent' | Critical | Phase 4 · W9–W10 (May 5 – May 18) | BorrowRepository – borrowItem(): atomic wallet update + BorrowRecord creation | TC-46: Confirm borrow → borrower −₩X, lender +₩X, item moves to Lent tab | Surjeet | Completed | Multi-device + Firebase Console
FR-40 | Transaction | Borrow is rejected if borrower credits < item price; Snackbar shown; nothing deducted | Critical | Phase 4 · W10 (May 12 – May 18) | BorrowRepository – borrowItem() credit check before any write operation | TC-47: Price > wallet → 'Insufficient credits' Snackbar; wallet balance unchanged | Surjeet | Completed | Manual Testing
FR-41 | Transaction | Each user has individual wallet node /wallets/{uid}/balance — balances are NOT shared | Critical | Phase 7 · W13 (Jun 2 – Jun 8) | BorrowRepository – observeWallet(uid) scoped to user UID; separate Firebase nodes | TC-48: Multiple users logged in → each sees only their own wallet balance | Surjeet | Completed | Multi-device Testing
FR-42 | Lent Item Detail | Lent item detail shows borrower name, phone, and location so lender can contact them | High | Phase 4 · W10 (May 12 – May 18) | LentItemDetailScreen – Borrower Details section (name, phone, locationAddress) | TC-49: Open lent item → borrower name, phone, and location all visible | Surjeet | Completed | Manual Testing
FR-43 | Return Flow | Two-step return: borrower requests → lender sees yellow banner → lender accepts → item → Available | Critical | Phase 4 · W10–W11 (May 12 – May 25) | BorrowRepository – requestReturn(); acceptReturn(); status → 'return_requested' then cleared | TC-50: Full 2-step flow tested end-to-end on two devices | Surjeet | Completed | Multi-device Testing
FR-44 | Return Flow | acceptReturn() writes LendHistory (lender) and BorrowHistory (borrower) on return accepted | High | Phase 5 · W11 (May 19 – May 25) | BorrowRepository – acceptReturn() writes to /lend_history and /borrow_history atomically | TC-51: Accept return → check both /lend_history and /borrow_history nodes in Firebase | Surjeet | Completed | Firebase Console
FR-45 | Notifications | FCM sends push notifications for: borrow, return request, return confirmed, reminder, penalty | High | Phase 5 · W11–W12 (May 19 – Jun 1) | LendLinkMessagingService.kt; BorrowRepository – notify() helper for all 5 types | TC-52: Each notification type triggered and received on physical device | Surjeet | Completed | Device Testing
FR-46 | Notifications | In-app Notifications screen lists all notification types with icon, title, body, timestamp | Medium | Phase 5 · W12 (May 26 – Jun 1) | NotificationsScreen composable; Firebase /notifications/{uid} listener | TC-53: Multiple notif types received → all appear correctly in Notifications screen | Surjeet | Completed | Manual Testing
FR-47 | Borrower History | Borrower Payment History records: '₩X paid for [Item] from [Lender]' and penalty deductions | High | Phase 5 · W11 (May 19 – May 25) | BorrowerHistoryScreens – PaymentHistoryScreen; BorrowRepository writes borrower_payment_history | TC-54: Borrow confirmed → Payment History entry with lender + item name | Surjeet | Completed | Manual Testing
FR-48 | Borrower History | Borrow History shows completed borrows only (post-return accepted) with lender phone and location | High | Phase 5 · W11–W12 (May 19 – Jun 1) | BorrowerHistoryScreens – BorrowHistoryScreen; acceptReturn() writes borrow_history | TC-55: Accept return → BorrowHistory card shows lender phone and location | Surjeet | Completed | Manual Testing
FR-49 | Bug Fix | itemId generated from push().key BEFORE photo upload starts — prevents 'item not found' error | Critical | Phase 7 · W12–W13 (May 26 – Jun 8) | ItemRepository – addItem(): push key first, then Storage upload to /item_images/{itemId}.jpg | TC-56: Add item → verify itemId node exists in Firebase before upload completes | Surjeet | Completed | Firebase Console
FR-50 | Bug Fix | 16 KB page size compliance — useLegacyPackaging=false in packaging{} block | High | Phase 7 · W13 (Jun 2 – Jun 8) | app/build.gradle.kts – packaging { jniLibs { useLegacyPackaging = false } } | TC-57: Build release AAB → upload to Play Console → no 16 KB alignment warning | Surjeet | Completed | Play Store Console
NFR-01 | Non-Functional | App targets Android API 35, minimum API 26 (Android 8.0 Oreo) | High | Phase 1 · W1–W2 (Mar 10 – Mar 23) | app/build.gradle.kts – minSdk=26, targetSdk=35, compileSdk=35 | TC-58: Install on API 26 emulator → app launches and all features work | Surjeet | Completed | Emulator Testing
NFR-02 | Non-Functional | App published on Google Play Store Internal Testing track by June 15 for professor evaluation | Critical | Phase 8 · W14 (Jun 9 – Jun 15) | Play Console – Internal Testing; signed AAB; professor Gmail added as tester | TC-59: Professor installs from opt-in URL on personal device → all features work | Surjeet | In Progress | Live Device Testing
NFR-03 | Non-Functional | All data syncs in real-time via Firebase ValueEventListener — no manual refresh needed | High | All phases | All repository files – callbackFlow + addValueEventListener + removeEventListener in awaitClose | TC-60: Lender adds item → borrower browse list updates within 3 seconds | Surjeet | Completed | Multi-device Testing
SUMMARY · Mar 10 – Jun 15, 2025 · Total Requirements: 53 Completed: 0 In Progress: 0 Completion Rate: 0%